## New Year
PREPARATION FOR NEW YEAR
Name Persons Responsible : Usha M Reddy
|  | Type | Send to | Status | Detail
BEGINNING OF YEAR
TAXES
|  | Annual Renewal | Gov Body |  | Secretary of State | www.sos.wa.gov/ccfs | admin@wapiusa.com | Copper.Head46
|  | 990N Taxes | Govbody |  | IRS | https://www.irs.gov/charities-non-profits/annual-electronic-filing-requirement-for-small-exempt-organizations-form-990-n-e-postcard | DirectorWAPI | Wapi4Wash#
FINANCES
|  | Year End Report of all WAPI finances | Govbody
UPDATE INFO
Update letter head with info
Update Govbody members
Update signature on file
Update Agenda and Minutes
UPDATE EVENT INFO
|  | Update Spring Info | to Govbody / webpage / facebook
|  | Update Picnic Info | to Govbody / webpage / facebook
|  | Update CME | to Govbody / webpage / facebook
|  | Update Winter Gala | to Govbody / webpage / facebook
|  | Update Other info | to Govbody / webpage / facebook
GOVBODY / Minutes
1st Q
2ndQ
3rd Q
GENBODY / Minutes
1st Q
2ndQ
3rd Q
END OF YEAR
FINANCES
Close Financial books
Complete Year End Financial Report
REPORTS
Complete all Minutes and file
YEAR END LETTER
|  | Ask President to write a New year report | Mail to genbody

## Networking
PREPARATION FOR NETWORKING EVENT
Name Persons Responsible
Event Committee members
Names of Volunteers
Project Manager : Usha M Reddy
Date
Venue
3 MONTH PRIOR TO EVENT - send info to Govbody |  | Responsibility | Status | Notes | Budget
Inform Govbody work has started
Confirm Date Place Food Menu
Prepare Entertainement agenda
Prepare budget
Email General body to keep the date open
Put Info on web
Put Info on Facebook, Linkedin
Start looking for program sponsors
1 MONTH PRIOR TO EVENT - send info to Govbody
Prepare Gen body Agenda and mail
Update Info on web
Update Info on Facebook & Linkedin
Send Flyer out
email General body details + Paypal arrangement
Confirm Sponsor arrangement
| Prepare list of volunteers | For Reception
For decorating place
For informing others
2 WEEKS PRIOR TO EVENT - send info to Govbody
Assign Volunteers
Prepare Speech outlines / pp
Confirm needs for wine
confirm food situation
Confirm Venue Audio Visual equipment
DAY OF EVENT
Set Up Event Registration booth
Print Event Registration Sheet for the Event
Bring In Box/tags/Cr slips/Pens/forms etc.
GenBody meeting and Upcoming Events
Social event
Dinner
Entertainement
Cleanup
POST EVENT - send info to Govbody
Complete minutes of Meetings
Send out Survey of stisfaction
Complete Event Report & Survey for Record
Thank You Email to Sponsors
Thank You Email Report to General Body
Thank You Email to Gov Body & Volunteers
Welcome Email to New Members
File away signIn sheets, Event report etc.
Put event report and minutes on web
PREPARATION FOR Event:
Chair, Social Event committee:
Commitee Member:
President:

## CME
2020 CME MILESTONES
Date of Event:
Place of Event: Swedish Issaquah Medical Center
CME Chair:
Activity Chair:
CME Committee:
Project Manager: Usha M Reddy
Co-Sponsor of Event:
PREPARATION FOR CME EVENT
Milestone 1: 1 year before Event: November of previous Year
dates:
Sanjiv Parikh
Book venue for meeting-Sanjiv Parikh
Milestone 2: 10 months before event December of Previous Year: CME Committee/Usha
12/01/2019 - 12/31/2019
CME Committee/Usha
President names the CME committee:
Select Theme / number of Speakers and Time for each speaker
Email Gov Body on info of CME, Theme, Talk time, previous survey
CME committee to narrows down and confirms Program Agenda
Start confirming speakers and obtain Topic Info & CV from speakers
Obtain latest application for CME sponsorship from UW
Milestone 3: 9 months before Event: Complete acquiring all info for application-CME Committee/Usha | [5 empty] | T
dates:
Complete acquiring all info for application-CME Committee/Usha
CV of CME Committee members
CV of all Speaker
Topic Info from all Speakers
Financial Disclosure CME Committee
Info for Grants Pharma
Signature on file CME Committee
Milestone 4: 8 months before Event
dates:
Complete and Submit Application Along with attachments for CME &fees to UW : Usha M Reddy
Budget timeline Grants
CME Brochure /
CME Flyer
CME Objectives /
CME Sign in
Conflict of Interest resolution /
Evaluation Form
Evaluation tools /
Expected Outcomes
Itemized budget
Mission Statement CME
Needs Assessment
Online CME Evaluation
Outcome Assessment Methodology
Planning Process/
Potential barriers /
Practice gap Analysis /
Program Agenda
Feedback Methodology
Timeline CME
Topic Info
Verbal Disclosure
Milestone 5: 7 - 5 months before Event
dates:
Usha M Reddy
Upon Approval by UW, activity number
Submit Financial Disclosure CME Committee
Submit Financial Disclosure Speakers
Mail faculty guidance to all Speakers
IRS 501
Current W9
Web & Facebook, LinkedIn update /
Start Applying for Grants
Start maintaining Exhibit Status & grant Log
Survey Monkey
Prepare Registration for CME
Start CME campaign -info / registration to all members and colleagues
Milestone 6: 4 months before Event
dates:
Usha M Reddy
Financial
Apply for exhibit space
Continue CME campaign
Continue updating Exhibit Status & grant Log
Start collecting info on Reps for exhibit space
Apply for exhibit space grants
Prepare Exhibit Space Requirements
Invitation
Application,
Receipt
CME Accreditation: Usha M Reddy
Prepare Survey Monkey
Registration
Milestone 7: 3 months before Event
dates:
Usha M Reddy
Financial: Usha M Reddy
Send info to UW regarding Grants and Exhibit Space
Continue updating Exhibit Status & grant Log
CME Accreditation: Usha M Reddy
Final Power Point Reminder to Speakers
Survey Monkey - prepare for CME-Usha M Reddy
Evaluation Survey
Registration detail
Pre & Post questionnaire with feedback
Continue CME campaign / monthly reminder
Milestone 8: 2 months before Event
dates:
CME Needs: Usha M Reddy - paper work to UW
Continue CME campaign / biweekly reminder
Continue updating Exhibit Status & grant Log
Speaker PowerPoint Presentation to UW
all Financial disclosures to UW
Peer Review signed by CME committee
Conflict of Interest Resolution forms for Speakers and CME Committee
all Financial disclosures to UW
ltr_of_agreement-Commercial Source
Milestone 1 week before Event
dates:
Finalize with Swedish: Sanjiv Parikh
Room Arrangements
Audio Visual Needs
Menu
Evening Social
Pre CME meeting: CME Committee/Usha
Assign Volunteers
President Welcome Speech
Confirm which doctors will introduce speakers
Confirm who will give gifts
Plan on gifts
Plan on evening Social
Who is getting Computers
Milestone 10: 3 days before event
dates:
Final Check of Event: Usha M Reddy
Volunteers
Let volunteers know their assignments
Confirm Printing assignment
Update web
Registration
Instruction
Evaluation
PowerPoint Presentation
CV of Speakers
CME Objectives
Milestone 9: Day of CME Event
dates:
Usha M Reddy / CME Committee/ Volunteers
Print and bring to Event: Dhara
Print Program Agenda x 50
Print Instructions x 50
Print Evaluation Forms x 5
Bring In Box/tags/Cr slips/Pens/forms etc.
Registration Desk: Dhara / Annette / Nandita
Set Up and Run Event Registration
Sign-in attendees, collect dues & instructions
Signatures for post PayPal CME Vendor Acknowledgement document
Course attendance verification
Gifts: Nandita
Gifts for each speaker with cards, Check
Give it to CME committee in a timely fashion
CME Needs: Usha
Bring pre & post questionnaires with answers x 5
Print Event Registration Sheet with PayPal info
CME Event: CME Committee
Welcome by President
Moderating CME Event - CME Committee
Timing of Speakers-Raksha
Getting Verbal disclosers signed by CME committee-Raksha
Evening Social: Sanjiv and Nandita
Welcome by Sanjiv
Finger food-Sanjiv and Nandita
Milestone 10: 1 week after event
dates:
Complete Post Event Activities: Usha M Reddy
Complete minutes of Meetings
Complete Event Report & Survey for Record
Thank You Email to Sponsors
Thank You Email Report to General Body
Thank You Email to Gov Body & Volunteers
Welcome Email to New Members
File away sign in sheets,
File away Event report etc.
Mail event report and minutes to Gen Body

## online CE
2021 ONLINE CE MILESTONES | [5 empty] | 2021 ONLINE CE - short list ( non cme)
Date of Event: | [5 empty] | Date of Event:
Place of Event: | [5 empty] | Chair: Amish Dave
CME Chair: | [5 empty] | Co- Chair
Activity Chair: | [5 empty] | Project Manager: Usha M Reddy
CME Committee: | [5 empty] | Co-Sponsor of Event: IAWW
Project Manager: Usha M Reddy
Co-Sponsor of Event: | [5 empty] | Title of Semimar
PREPARATION FOR CME EVENT | [5 empty] | Speaker 1
Milestone 1: 2months before event December of Previous Year: CME Committee/Usha | [6 empty] | Name
| Dates | [5 empty] | Affiliation
|  |  | President Calls for a zoom meeting to all Gov body members - regarding upcoming CE Event |  |  |  | Topic
|  |  | President names 2 members in charge of the currentevent |  |  |  | 2 Objectives
Select Theme /Speakers and Time for each speaker / Panel Speakers
Email Gov Body / IAWW on info of CE, Theme, Talk time,
Start confirming speakers and obtain Topic Info & CV from speakers
Obtain info on possible grants
Milestone 2:1 months before Event: Complete acquiring all info for application-CME Committee/Usha |  |  |  |  | T
dates:
Complete acquiring all info for application-CME Committee/Usha
CV of CME Committee members
CV of all Speaker
Topic and Objectives Info from all Speakers
Prepare
Itemized budget
CME Brochure /
CME Flyer
Registration Info
Evaluation Form
Inform IAWW
Send Brochure and flyers
Milestone 3 Upto Even6
dates:
Usha M Reddy
Submit Itemized Budget CME Committee / Gov body
Survey Monkey
Prepare Registration for Event
PrepareEvaluation Questionnaire for Event activity
Start CME campaign -info / registration to all members and colleagues
Milestone 6: Event
dates:
Coordinate
IAWW
Speakers
Panel Members
Send reminder email to
IAWW tech
Speakers, Panel members and those registered
designated Committee members to take charge of Event
Milestone 7: post Event
dates:
Usha M Reddy
Evaluation: Usha M Reddy
Prepare Evaluation report
Send report first to govbody mrmbers
Send report registered and life members
File report

## Fitness &health
PREPARATION FOR FITNESS & HEALTH EVENT
Name Persons Responsible
Event Committee members
Names of Volunteers
Project Manager : Usha M Reddy
Date
Venue
3 MONTH PRIOR TO EVENT - send info to Govbody |  | Responsibility | Status | Notes | Budget
Inform Govbody work has started
Confirm Date Place Food Menu
Prepare Entertainement agenda
Prepare budget
Email General body to keep the date open
Put Info on web
Put Info on Facebook, Linkedin
Start looking for program sponsors
1 MONTH PRIOR TO EVENT - send info to Govbody
Prepare Gen body Agenda and mail
Update Info on web
Update Info on Facebook & Linkedin
Send Flyer out
email General body details + Paypal arrangement
Confirm Sponsor arrangement
| Prepare list of volunteers | For Reception
For decorating place
For informing others
2 WEEKS PRIOR TO EVENT - send info to Govbody
Assign Volunteers
Prepare Speech outlines / pp
Confirm needs for wine
confirm food situation
Confirm Venue Audio Visual equipment
DAY OF EVENT
Set Up Event Registration booth
Print Event Registration Sheet for the Event
Bring In Box/tags/Cr slips/Pens/forms etc.
GenBody meeting and Upcoming Events
Social event
Dinner
Entertainement
Cleanup
POST EVENT - send info to Govbody
Complete minutes of Meetings
Send out Survey of stisfaction
Complete Event Report & Survey for Record
Thank You Email to Sponsors
Thank You Email Report to General Body
Thank You Email to Gov Body & Volunteers
Welcome Email to New Members
File away signIn sheets, Event report etc.
Put event report and minutes on web
PREPARATION FOR Event:
Chair, Social Event committee:
Commitee Member:
President:

## Wintergala
PREPARATION FOR WINTER GALA EVENT
Name Persons Responsible
Event Committee members
Names of Volunteers
Project Manager : Usha M Reddy
Date
Venue
3 MONTH PRIOR TO EVENT - send info to Govbody |  | Responsibility | Status | Notes | Budget
Inform Govbody work has started
Confirm Date Place Food Menu
Prepare Entertainement agenda
Prepare budget
Put Info on web
Put Info on Facebook
Email General body to keep the date open
Start looking for program sponsors
1 MONTH PRIOR TO EVENT - send info to Govbody
Prepare Gov body Agenda and mail
Send Nomination for next Years posts
Send Flier out
email General body details + Paypal arrangement
Confirm Sponsor arrangement
2 WEEKS PRIOR TO EVENT - send info to Govbody
Assign Volunteers
Prepare Speech outlines / pp
Resend Nominations and program details
Confirm Venue Audio Visual equipment
DAY OF EVENT
Set Up Event Registration booth
Print Event Registration Sheet for the Event
Bring In Box/tags/Cr slips/Pens/forms etc.
GovBody meeting and Elections
General body Meeting - Announce new Govbody
Secretary- Take Minutes of both Gov and General
Entertainement
POST EVENT - send info to Govbody
Complete minutes of Meetings
Send out Survey of stisfaction
Complete Event Report & Survey for Record
Thank You Email to Sponsors
Thank You Email Report to General Body
Thank You Email to Gov Body & Volunteers
Welcome Email to New Members
File away signIn sheets, Event report etc.
Put event report and minutes on web
PREPARING FOR NEW YEAR
Type New Presidents Welcome Letter
Old Presidents Thank You Letter
Start CME process
Plan on 1st Govbody meeting for next year

## Picnic
PREPARATION FOR PICNIC EVENT
Name Persons Responsible
Event Committee members
Names of Volunteers
Project Manager : Usha M Reddy
Date
Venue
3 MONTH PRIOR TO EVENT - send info to Govbody |  | Responsibility | Status | Notes | Budget
Confirm Date Place Food Menu
Find Place and Food menum for date
Money transactions
Prepare Picnic agenda
Details info of picnic
Put info on web
Put info on Facebook
Prepare Picnic Flyer
Get Itemized budget ready
Get sponsor to cover your budget
1 MONTH PRIOR TO EVENT - send all info to govbody
Newsletter
Flyers
Web Info
Facebook info
Banner
Signs
Update on financial status
2 WEEKS PRIOR TO EVENT - send info to govbody
Assign Volunteers for Calling List
Assign Volunteers for activiies
Booth for new membership
Booth for upcoming events
Final Reconfirm- Date/place/food etc
Confirm Entertainment requirements
DAY OF EVENT
Set Up Event Registration booth Sheet
Responsible for registration
Responsible for money collection
Responsible for newmember entry to database
Responsible for entering names of participants in database
Bring In Box/tags/Cr slips/Pens/forms etc.
Take Minutes
POST EVENT - send info to govbody
Complete minutes of Meetings
Complete Event Report & Survey for Record
Thank You Email to Sponsors
Thank You Email Report to General Body
Thank You Email to Gov Body & Volunteers
Welcome Email to New Members
File away signIn sheets, Event report etc.
Enter registrants to web event registration
Put event report and minutes on web

## Spring Social
PREPARATION FOR SPRING SOCIAL EVENT
Name Persons Responsible
Event Committee members
Names of Volunteers
Project Manager : Usha M Reddy
Date
Venue
3 MONTH PRIOR TO EVENT - send info to Govbody |  | Responsibility | Status | Notes | Budget
Inform Govbody work has started
Confirm Date Place Food Menu
Prepare Entertainement agenda
Prepare budget
Email General body to keep the date open
Put Info on web
Put Info on Facebook
Start looking for program sponsors
1 MONTH PRIOR TO EVENT - send info to Govbody
Prepare Gen body Agenda and mail
Update Info on web
Update Info on Facebook
Send Flier out
email General body details + Paypal arrangement
Confirm Sponsor arrangement
| Prepare list of volunteers | For Reception
For decorating place
For informing others
2 WEEKS PRIOR TO EVENT - send info to Govbody
Assign Volunteers
Prepare Speech outlines / pp
Confirm needs for wine
confirm food situation
Confirm Venue Audio Visual equipment
DAY OF EVENT
Set Up Event Registration booth
Print Event Registration Sheet for the Event
Bring In Box/tags/Cr slips/Pens/forms etc.
GenBody meeting and Upcoming Events
Social event
Dinner
Entertainement
Cleanup
POST EVENT - send info to Govbody
Complete minutes of Meetings
Send out Survey of stisfaction
Complete Event Report & Survey for Record
Thank You Email to Sponsors
Thank You Email Report to General Body
Thank You Email to Gov Body & Volunteers
Welcome Email to New Members
File away signIn sheets, Event report etc.
Put event report and minutes on web
PREPARATION FOR Event:
Chair, Social Event committee:
Commitee Member:
President:

## LM-Aprreciation
PREPARATION FOR LIFE MEMBER APPRECIATION EVENT
Name Persons Responsible
Event Committee members
Names of Volunteers
Project Manager : Usha M Reddy
Date
Venue
3 MONTH PRIOR TO EVENT - send info to Govbody |  | Responsibility | Status | Notes | Budget
Inform Govbody work has started
Confirm Date Place Food Menu
Prepare Entertainement agenda
Prepare budget
Email General body to keep the date open
Put Info on web
Put Info on Facebook, Linkedin
Start looking for program sponsors
1 MONTH PRIOR TO EVENT - send info to Govbody
Prepare Gen body Agenda and mail
Update Info on web
Update Info on Facebook & Linkedin
Send Flyer out
email General body details + Paypal arrangement
Confirm Sponsor arrangement
| Prepare list of volunteers | For Reception
For decorating place
For informing others
2 WEEKS PRIOR TO EVENT - send info to Govbody
Assign Volunteers
Prepare Speech outlines / pp
Confirm needs for wine
confirm food situation
Confirm Venue Audio Visual equipment
DAY OF EVENT
Set Up Event Registration booth
Print Event Registration Sheet for the Event
Bring In Box/tags/Cr slips/Pens/forms etc.
GenBody meeting and Upcoming Events
Social event
Dinner
Entertainement
Cleanup
POST EVENT - send info to Govbody
Complete minutes of Meetings
Send out Survey of stisfaction
Complete Event Report & Survey for Record
Thank You Email to Sponsors
Thank You Email Report to General Body
Thank You Email to Gov Body & Volunteers
Welcome Email to New Members
File away signIn sheets, Event report etc.
Put event report and minutes on web
PREPARATION FOR Event:
Chair, Social Event committee:
Commitee Member:
President:

## Walkathon
PREPARATION FOR WALKATHON EVENT
Name Persons Responsible
Event Committee members
Names of Volunteers
Project Manager : Usha M Reddy
Date
Venue
PREPARATION FOR PICNIC - send info to govbody |  | Name of person Responsible | Status
Inform Govbody work has started
Confirm Date Place Food Menu
Find Place and Food menum for date
Money transactions
Prepare Walkathon agenda
Details info of Walkathon
Prepare Walkathon Flyer
Get Itemized budget ready
Get sponsor to cover your budget
1 MONTH PRIOR TO EVENT - send all info to govbody
Newsletter
Flyers
Web Info
Banner
Signs
Update on financial status
2 WEEKS PRIOR TO EVENT - send info to govbody
Assign Volunteers for Calling List
Assign Volunteers for activiies
Booth for new membership
Booth for upcoming events
Final Reconfirm- Date/place/food etc
Confirm Entertainment requirements
DAY OF EVENT
Set Up Event Registration booth Sheet
Responsible for registration
Responsible for money collection
Responsible for newmember entry to database
Responsible for entering names of participants in database
Bring In Box/tags/Cr slips/Pens/forms etc.
Take Minutes
POST EVENT - send info to govbody
Complete minutes of Meetings
Complete Event Report & Survey for Record
Thank You Email to Sponsors
Thank You Email Report to General Body
Thank You Email to Gov Body & Volunteers
Welcome Email to New Members
File away signIn sheets, Event report etc.
Enter registrants to web event registration
Put event report and minutes on web

## Election
PREPARATION FOR ELECTION EVENT
Name Persons Responsible
Event Committee members
Names of Volunteers
Project Manager : Usha M Reddy
Date
Venue
PREPARATION FOR MEETING & ELECTION |  |  | Name of person responsible | Status | Notes | Budget
Inform Govbody work has started
Election & Gen Body Announcement x3 by emails
1 email
2nd email
3rd email
Confirm Date Place Food Menu
Find Place and Food menum for date
Money transactions
Upload event info to website
Election announcement
Sponsor and speaker for talk
Agenda for Gov / Gen Body meeting by end of Jan
2 WEEKS PRIOR TO EVENT
Prepare Speech outlines / pp
President
Election Officer
Final Reconfirm- Date/place/food etc (2 wk prior)
Confirm Audio Visual equipment
Final Reconfirmation w/ sponsor(1-2 wk prior)
Get agreement of payment from speaker
DAY OF EVENT
Set Up Event Registration booth Sheet
Print Election Sheet, Report Sheet & Agendas
Print Dues Paid List for the Event (2)
Print Event Registration Sheet for the Event (1)
Bring In Database Update Folder to event
Bring In Box/tags/Cr slips/Pens/forms etc.
Complete Election Sheet for Record
Bring In Speech Outlines
Gov body meeting
Gen body meeting
Conduct election
Take Minutes
Talk
POST EVENT
Complete minutes of Meetings
Complete Event Report & Survey for Record
Thank You Email to Sponsors
Thank You Email Report to General Body
Thank You Email to Gov Body & Volunteers
Welcome Email to New Members
File away signIn sheets, Event report etc.
Put event report and minutes on web